## Query log
Tender clarification pack: query log
Sample. 17 of the 23 queries from a real review of an overseas river bridge, drawn from Arched's published case studies, with project names, places and client details removed. AI first pass, checked and signed off by an engineer. arched.ai
Ref | Sheet / clause | Query | Basis adopted meanwhile | Effect if it changes | Action
Q-01 | GA-01 pier plan / side view | Pier pile cap is 5100 x 5100 on plan and section, but the side view dimensions sum to 5000 (1400 + 2200 + 1400). The side view also shows a foundation level (RL 78.300) that matches no pier. Confirm the cap size and founding levels. | 5100 x 5100; founding levels pier by pier from the elevation and note 16. | 5000 cap: 9.1 m³ less reinforced concrete across the pier caps. | Query
Q-02 | GA-01 borehole logs | Rock levels at P2, P3 and P4 (79.94 / 77.57 / 75.20) are an exact straight-line interpolation between boreholes B2 and B3. There is no borehole at these piers. Confirm founding levels, or provide boreholes. | Interpolated levels; confirmatory boreholes included as separate items. | Each 1 m change in rock level changes pile, casing and reinforcement length at that pier. | Query + state
Q-03 | GA-01 borehole B1 | At abutment A1, borehole B1 logs 12.7 m of 'coarse sand (no core)' from RL 82.95 to 70.25, while P1, 25 m away, meets rock at RL 82.31. This may be weathered rock or core loss. Confirm, or re-bore A1. | Friction piles at A1 as drawn; re-bore included. | If A1 piles can be socketed into rock, they shorten and the friction pile test category falls away. | Query
Q-04 | GA-01 abutment section | The 10.0 m wedge behind each abutment is hatched and labelled 'filter media'; 'granular material' labels the fill beyond. Confirm whether the whole wedge is filter media or a 600 mm filter layer against granular fill. | Whole wedge as filter media: 471 m³. | Filter layer only: most of the 471 m³ becomes granular fill, a cheaper material. | Query
Q-05 | Spec. piling / rates schedule | The specification includes installing piles for initial load tests in the pile rate, but the rates schedule prices the tests and not the trial piles. Confirm how trial piles are paid. | 4 trial piles (93.8 m) measured as separate items. | 4 piles, 93.8 m, with casing and reinforcement. | State in bid
Q-06 | GA-01 notes | Pile design load is not given, and the initial load test is paid per tonne of test load. Confirm the design load. | Indicative test load from vertical load and braking. | Test load and test cost follow the design load. | Query
Q-07 | GA-01 note 25 | Note 25 gives a safe bearing capacity of 60 t/m² (about 590 kPa) for end bearing, about 68 t (670 kN) on a 1.2 m pile. Rock socket capacity is not stated. Designer to confirm. | Not used in quantities. | Design issue: affects pile length and number. | Query
Q-08 | GA-01 pile detail; spec. casings | Permanent casings are shown full depth to rock. The specification requires them at least to maximum scour level (piers RL 89.73, abutments RL 93.91). Confirm the casing depth. | Full depth to rock, as drawn: 707 m of casing (126 t). | Casing to scour level only: a large share of the 707 m falls away. Raise as value engineering. | Query (VE)
Q-09 | GA-01 notes | Concrete grades are given for piles only. Confirm grades for pile caps, piers, pier caps, abutments and deck. | Pile caps, piers, pier caps and deck C28/35; abutments C25/30 (M35 and M30 in the source notation). | A grade step in the deck changes the price of 1,238 m³ of concrete. | Query
Q-10 | Drawing register | No reinforcement drawings or bar schedules are issued. Confirm whether they will be issued before award. | Reinforcement allowances: piles 120 kg/m³, deck 230 kg/m³, others as listed. | A 10% change in steel is about 52 t. | State in bid
Q-11 | GA-01 abutment (NTS) | Abutment cap width is not dimensioned. The approach slab is drawn between the rear wall and ballast wall (5.9 m), but note 18 refers to the standard approach slab. Confirm both. | Cap 1.0 m wide; approach slab 5.9 m x 12 m. | Standard slab extending 3.5 m onto the backfill: about 25 m³ more reinforced concrete. | Query
Q-12 | GA-01 deck section; spec. surfacing | Wearing course is drawn as 50 mm bituminous concrete + 25 mm mastic asphalt; the specification's standard type is 40 + 25. Bitumen grade is not stated. | 50 + 25 as drawn. | Thickness and binder grade change the surfacing price over 1,793 m². | Query
Q-13 | GA-01 bearing layout | Bearing capacities (fixed, free, guided) are not given. End-span bearings sit 480 mm from the joint at the abutments against 625 mm at the piers. | 48 bearings at 150 t (about 1,500 kN) capacity each. | Bearings are priced by capacity: 200 t (about 2,000 kN) bearings cost materially more. | Query
Q-14 | GA-01 elevation | No river protection (apron or pitching) is shown, although the design flood level (RL 101.2) is above bank level at both abutments and abutment scour level is RL 93.91. | Indicative apron and pitching items listed separately, outside the drawn scope. | Design required; a scope gap if left out. | State in bid
Q-15 | GA-01 pier cap | Seismic or transverse restrainers on the pier caps are not shown. | Excluded. | Add if the designer requires them. | State in bid
Q-16 | GA-01 borehole logs | Drawing errors: borehole B3 bottom level printed RL 87.820 (reads as 67.820), B4 RL 89.600 (69.600); B3 and B4 overall depths do not add up; B2 layer depths conflict with the levels. | Not used for quantities. | None on price. Correct the drawing. | Note
Q-17 | GA-01 plan | Approach roads are shown on the GA (203.5 m and 278.5 m). | Excluded: priced separately. | Outside this package. | State in bid

## Assumptions
Assumptions and exclusions to state
Sample. 17 of the 23 queries from a real review of an overseas river bridge, drawn from Arched's published case studies, with project names, places and client details removed. AI first pass, checked and signed off by an engineer. arched.ai
No. | Assumption or exclusion
01 | Pier pile caps taken as 5100 x 5100 mm, as on plan and section (Q-01).
02 | Founding levels at P2 to P4 taken from interpolated rock levels; pile lengths subject to confirmatory boreholes (Q-02).
03 | Abutment A1 priced as friction piles as drawn (Q-03).
04 | Trial piles for initial load tests measured and priced as separate items (Q-05).
05 | Permanent casings priced full depth to rock as drawn (Q-08).
06 | Concrete grades assumed as stated where the drawings are silent (Q-09).
07 | Reinforcement priced on allowances pending bar schedules; remeasured on issue (Q-10).
08 | Bearings priced at 150 t (about 1,500 kN) capacity each; capacities to be confirmed (Q-13).
09 | River protection, seismic restrainers and approach roads excluded (Q-14, Q-15, Q-17).

## Key quantities
Key quantities
Sample. 17 of the 23 queries from a real review of an overseas river bridge, drawn from Arched's published case studies, with project names, places and client details removed. AI first pass, checked and signed off by an engineer. arched.ai
Element | Quantity | Basis
Bored piles, 1200 mm | 42 nr | 975 m concreted length, including 4 trial piles
Permanent steel casing, 6 mm | 707 m | 126 t; full depth to rock as drawn (Q-08)
Pile caps, reinforced concrete | 579 m³
Piers, pier caps and bearing plinths | 228 m³
Box abutments | 140 m³ | Walls, ballast wall, front wall and cap
Deck: T-beams and slab | 1,238 m³ | Six 25 m spans
Reinforcement | 518 t | Allowance pending bar schedules (Q-10)
Bearings | 48 nr | 150 t (about 1,500 kN) capacity assumed (Q-13)
Expansion joints | 84 m | Strip seal
Deck surfacing | 1,793 m² | 50 mm + 25 mm as drawn (Q-12)

## POMI BOQ (Gulf)
BOQ excerpt to POMI: bridge foundations and substructure
Sample. 17 of the 23 queries from a real review of an overseas river bridge, drawn from Arched's published case studies, with project names, places and client details removed. AI first pass, checked and signed off by an engineer. arched.ai
Clause | Item description | Unit | Quantity | Rate | Amount
Section A: General requirements
A8 | Temporary works: de-watering to pile cap excavations at river-bed piers P2 to P4 | item | 1
Section B: Site work
B8.4 | Earthwork support to pile cap excavations | item | 1
B9 | Trench excavation to receive pile caps, commencing at existing ground level | m³ | 671.7
B15.3 | Permanent steel lining, 6 mm thick, to 1200 mm diameter piles, to rock level (42 nr) | m | 707.1
B15.5 | Concrete filling to 1200 mm diameter bored piles, grade C28/35 | m³ | 1102.8
B15.6 | Cutting off tops of piles | nr | 42
B18 | Testing piling: low-strain integrity testing of piles (42 nr) | item | 1
B18 | Testing piling: trial piles and initial load tests (4 nr, 93.8 m) | item | 1
Section C: Concrete work
C2.3 | Plain poured concrete in blinding, 100 mm thick, below pile caps, grade as specified | m³ | 28.8
C2.2 | Reinforced poured concrete grade C28/35 in pile caps | m³ | 578.6
C2.11 | Reinforced poured concrete grade C28/35 in bridge piers, pier caps and bearing plinths | m³ | 227.5
C2.11 | Reinforced poured concrete in bridge abutment walls and caps, grade as specified | m³ | 140.2
C3.2 | High yield deformed bar reinforcement to BS 4449 in piles and pile caps; diameters stated on issue of bar schedules (provisional) | t | 184.4
C3.2 | Ditto in piers and abutments (provisional) | t | 48.8

## CESMM4 bill (UK)
Bill excerpt to CESMM4: bridge foundations and substructure
Sample. The river bridge in Arched's published case studies, measured to CESMM4; project details removed. AI first pass, checked and signed off by an engineer. arched.ai
Number | Item description | Unit | Quantity | Rate | Amount
Class E: Earthworks
Excavation for foundations; material other than topsoil, rock or artificial hard material; pile caps, around pile shafts
E324.1 | Maximum depth 1–2 m: abutments A1, A2, pier P5 | m³ | 493.2
E325 | Maximum depth 2–5 m: pier P1 | m³ | 92.7
Ditto, below the river (the body of water identified in the Preamble); Commencing Surface river bed
E322 | Maximum depth 0.25–0.5 m: pier P2 | m³ | 12.8
E324.2 | Maximum depth 1–2 m: piers P3, P4 | m³ | 72.9
Excavation ancillaries
E522 | Preparation of excavated surfaces, material other than topsoil, rock or artificial hard material: below blinding to pile caps | m² | 288.2
E532 | Disposal of excavated material other than topsoil, rock or artificial hard material | m³ | 671.7
Class F: In situ concrete
Provision of concrete; designed mix to BS 8500-2 and Specification Series 1700; cement to BS EN 197-1; 20 mm aggregate; exposure class as Appendix 17/1
F122 | Strength class C12/15: blinding | m³ | 28.8
F152 | Strength class C25/30: abutments | m³ | 140.2
F162 | Strength class C28/35: pile caps, piers and pier caps | m³ | 796.7
Placing of mass concrete
F611 | Blinding, thickness not exceeding 150 mm, below pile caps | m³ | 28.8
Placing of reinforced concrete
F724 | Bases, footings, pile caps and ground slabs, thickness exceeding 500 mm: pile caps | m³ | 578.6
F742 | Walls, thickness 150–300 mm: abutment rear, side, inner and dirt walls | m³ | 121.5
F743 | Walls, thickness 300–500 mm: abutment front walls, 400 mm | m³ | 6.7
F764 | Beams, cross-sectional area 0.25–1 m²: abutment caps, 1000 × 500 mm | m³ | 12
F755 | Columns and piers, cross-sectional area exceeding 1 m²: circular piers, 2200 mm diameter | m³ | 53.2
F766 | Special beam sections: pier caps PC1 to PC5, crosshead 10.0 × 2.5 m, 0.75 m deep at the ends and 1.5 m at the pier, on a 2.5 × 2.5 × 0.4 m bottom block | m³ | 164.8
Class G: Concrete ancillaries
Formwork; rough finish, Class F1 to Specification Series 1700: faces to be buried or hidden
G144 | Plane vertical, width 0.4–1.22 m: abutment pile cap sides, two 900 mm tiers; inner face of abutment front walls, 700 mm | m² | 158.6
G145 | Plane vertical, width exceeding 1.22 m: pier pile cap sides, 1800 mm; abutment rear walls, inner walls, inner faces of side and dirt walls | m² | 869.5
Formwork; other stated finish, Class F3 to Specification Series 1700: exposed faces
G315 | Plane horizontal, width exceeding 1.22 m: soffits of bottom blocks to pier caps, outside the pier | m² | 12.2
G325 | Plane sloping, width exceeding 1.22 m: soffits of pier cap cantilevers | m² | 95.6
G343 | Plane vertical, width 0.2–0.4 m: sides of bottom blocks to pier caps, 400 mm | m² | 20
G344 | Plane vertical, width 0.4–1.22 m: pier cap sides, depth varying 0.75–1.5 m, and ends, 750 mm; abutment cap sides, 500 mm; outer face of abutment front walls, 700 mm | m² | 183.4
G345 | Plane vertical, width exceeding 1.22 m: outer faces of abutment side walls; front faces of dirt walls | m² | 177.4
G355 | Curved to one radius in one plane, radius 1100 mm, width exceeding 1.22 m: circular piers | m² | 96.8
Class P: Piles
Bored cast in place concrete piles, diameter 1200 mm; concrete designed mix C28/35, 20 mm aggregate (1,102.8 m³ in all, included in the rates)
Commencing Surface existing ground: abutments A1, A2; piers P1, P5
P161.1 | Number of piles | nr | 26
P162.1 | Concreted length | m | 649.3
P163.1 | Depth bored to a maximum depth of 29 m | m | 702.6
Commencing Surface existing river bed: piers P2 to P4
P161.2 | Number of piles | nr | 12
P162.2 | Concreted length | m | 232
P163.2 | Depth bored to a maximum depth of 23 m | m | 242.5
Preliminary piles, for initial load tests (2 end-bearing, 2 friction); Commencing Surface existing ground
P161.3 | Number of piles | nr | 4
P162.3 | Concreted length, to working-pile cut-off level | m | 93.8
P163.3 | Depth bored to a maximum depth of 28 m | m | 100.7
Class Q: Piling ancillaries
Cast in place concrete piles, diameter 1200 mm
Q126.1 | Backfilling empty bore with excavated material: working piles | m | 63.9
Q126.2 | Backfilling empty bore with excavated material: preliminary piles | m | 6.9
Q136 | Permanent casings, 6 mm steel to BS EN 10025 S275, uncoated, each length not exceeding 13 m | m | 105.4
Q146 | Permanent casings, 6 mm steel to BS EN 10025 S275, uncoated, each length exceeding 13 m | m | 672.5
Q176 | Cutting off surplus lengths, including permanent casing: working piles (600 mm cast above cut-off level) | m | 22.8
Q186 | Preparing heads: working piles | nr | 38
Pile tests
Q815 | Maintained loading with kentledge reaction; test load 420 t (4,120 kN): preliminary friction piles | nr | 2
Q816 | Maintained loading with kentledge reaction; test load 720 t (7,060 kN): preliminary end-bearing piles | nr | 2
Q840.1 | Non-destructive integrity tests, low strain: working piles | nr | 38
Q840.2 | Non-destructive integrity tests, low strain: preliminary piles | nr | 4
Note 01. Excerpt only: dewatering and cofferdams at the river-bed piers P2 to P4 are method-related charges (Class A), and filling is measured on the full bill once founding and formation levels are confirmed (clarification pack queries 02 and 03).
Note 02. Reinforcement is not billed here. CESMM4 measures it by bar size (G52-, and Q21- in piles), and the drawings give no bar schedules (clarification pack query 10). The estimate carries provisional allowances of 184 t in foundations and 49 t in substructure; 49 t is light for the pier caps and will be revisited with the schedules.
Note 03. Concrete grades are as drawn: C28/35 for piles, pile caps, piers and pier caps, and C25/30 for the abutments. For a UK river crossing, C32/40 is more usual where de-icing salts or freeze-thaw apply; to be confirmed with the designer.
Note 04. Bearing plinths and the sand filling to the abutment cells are measured on the full bill.
Note 05. Depth bored is from the Commencing Surface to the pile toe; concreted length from cut-off level to toe; permanent casing from the Commencing Surface to the bottom of the casing, so it totals 777.9 m here against 707.1 m measured from cut-off level. Preliminary piles are assumed at representative supports (2 end-bearing, 2 friction) pending their locations.

## BS 8666 schedule
Bar schedule WW101A to BS 8666:2020: cantilever wing wall, 8.0 m, falling 6.0 m to 2.0 m (this schedule conforms to BS 8666:2020)
Sample. A real wing wall drawing re-presented to BS 8666:2020, every bar scheduled; project details removed. AI first pass, checked and signed off by an engineer. arched.ai
Member | Bar mark | Type and size | No. of mbrs | No. of bars in each | Total no. | Length of each bar (mm) | Shape code | A | B | C | D | E/R | Rev | Mass (kg)
Stem, ch 0–1,000: earth face, verticals (dwg a1) | 01a | H20 | 1 | 1 | 1 | 6475 | 11 | 6220 | 300 |  |  |  | -
Stem, ch 0–1,000: earth face, verticals (dwg a1) | 01b | H20 | 1 | 1 | 1 | 6325 | 11 | 6060 | 300 |  |  |  | -
Stem, ch 0–1,000: earth face, verticals (dwg a1) | 01c | H20 | 1 | 1 | 1 | 6150 | 11 | 5900 | 300 |  |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a1) | 02a | H16 | 1 | 1 | 1 | 6175 | 21 | 185 | 5740 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a1) | 02b | H16 | 1 | 1 | 1 | 6025 | 21 | 185 | 5595 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a1) | 02c | H16 | 1 | 1 | 1 | 5875 | 21 | 185 | 5450 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a1) | 02d | H16 | 1 | 1 | 1 | 5750 | 21 | 185 | 5305 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a1) | 02e | H16 | 1 | 1 | 1 | 5600 | 21 | 185 | 5160 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a1) | 02f | H16 | 1 | 1 | 1 | 5450 | 21 | 185 | 5015 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a1) | 02g | H16 | 1 | 1 | 1 | 5300 | 21 | 185 | 4875 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a1) | 03a | H16 | 1 | 1 | 1 | 5150 | 21 | 185 | 4725 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a1) | 03b | H16 | 1 | 1 | 1 | 5000 | 21 | 185 | 4575 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a1) | 03c | H16 | 1 | 1 | 1 | 4850 | 21 | 185 | 4425 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a1) | 03d | H16 | 1 | 1 | 1 | 4700 | 21 | 185 | 4275 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a1) | 03e | H16 | 1 | 1 | 1 | 4550 | 21 | 185 | 4125 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a1) | 03f | H16 | 1 | 1 | 1 | 4400 | 21 | 185 | 3975 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a1) | 03g | H16 | 1 | 1 | 1 | 4250 | 21 | 185 | 3825 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a1) | 04a | H12 | 1 | 1 | 1 | 4125 | 21 | 185 | 3675 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a1) | 04b | H12 | 1 | 1 | 1 | 3950 | 21 | 185 | 3495 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a1) | 04c | H12 | 1 | 1 | 1 | 3775 | 21 | 185 | 3315 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a1) | 04d | H12 | 1 | 1 | 1 | 3575 | 21 | 185 | 3135 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a1) | 04e | H12 | 1 | 1 | 1 | 3400 | 21 | 185 | 2955 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a1) | 04f | H12 | 1 | 1 | 1 | 3225 | 21 | 185 | 2775 | 300 |  |  | -
Stem, ch 7,000–8,000: earth face, verticals (dwg a1) | 05a | H12 | 1 | 1 | 1 | 3050 | 21 | 185 | 2595 | 300 |  |  | -
Stem, ch 7,000–8,000: earth face, verticals (dwg a1) | 05b | H12 | 1 | 1 | 1 | 2850 | 21 | 185 | 2395 | 300 |  |  | -
Stem, ch 0–1,000: earth face, verticals (dwg a2) | 06a | H20 | 1 | 1 | 1 | 6400 | 11 | 6140 | 300 |  |  |  | -
Stem, ch 0–1,000: earth face, verticals (dwg a2) | 06b | H20 | 1 | 1 | 1 | 6225 | 11 | 5980 | 300 |  |  |  | -
Stem, ch 0–1,000: earth face, verticals (dwg a2) | 06c | H20 | 1 | 1 | 1 | 6075 | 11 | 5820 | 300 |  |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a2) | 07a | H16 | 1 | 1 | 1 | 6100 | 21 | 185 | 5660 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a2) | 07b | H16 | 1 | 1 | 1 | 5950 | 21 | 185 | 5515 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a2) | 07c | H16 | 1 | 1 | 1 | 5800 | 21 | 185 | 5370 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a2) | 07d | H16 | 1 | 1 | 1 | 5650 | 21 | 185 | 5225 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a2) | 07e | H16 | 1 | 1 | 1 | 5525 | 21 | 185 | 5080 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a2) | 07f | H16 | 1 | 1 | 1 | 5375 | 21 | 185 | 4940 | 300 |  |  | -
Stem, ch 1,000–3,000: earth face, verticals (dwg a2) | 07g | H16 | 1 | 1 | 1 | 5225 | 21 | 185 | 4795 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a2) | 08a | H12 | 1 | 1 | 1 | 5100 | 21 | 185 | 4645 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a2) | 08b | H12 | 1 | 1 | 1 | 4950 | 21 | 185 | 4495 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a2) | 08c | H12 | 1 | 1 | 1 | 4800 | 21 | 185 | 4345 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a2) | 08d | H12 | 1 | 1 | 1 | 4650 | 21 | 185 | 4195 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a2) | 08e | H12 | 1 | 1 | 1 | 4500 | 21 | 185 | 4045 | 300 |  |  | -
Stem, ch 3,000–5,000: earth face, verticals (dwg a2) | 08f | H12 | 1 | 1 | 1 | 4350 | 21 | 185 | 3895 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a2) | 09a | H12 | 1 | 1 | 1 | 4200 | 21 | 185 | 3745 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a2) | 09b | H12 | 1 | 1 | 1 | 4025 | 21 | 185 | 3565 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a2) | 09c | H12 | 1 | 1 | 1 | 3825 | 21 | 185 | 3385 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a2) | 09d | H12 | 1 | 1 | 1 | 3650 | 21 | 185 | 3205 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a2) | 09e | H12 | 1 | 1 | 1 | 3475 | 21 | 185 | 3025 | 300 |  |  | -
Stem, ch 5,000–7,000: earth face, verticals (dwg a2) | 09f | H12 | 1 | 1 | 1 | 3300 | 21 | 185 | 2845 | 300 |  |  | -
Stem, ch 7,000–8,000: earth face, verticals (dwg a2) | 10a | H12 | 1 | 1 | 1 | 3125 | 21 | 185 | 2665 | 300 |  |  | -
Stem, ch 7,000–8,000: earth face, verticals (dwg a2) | 10b | H12 | 1 | 1 | 1 | 2925 | 21 | 185 | 2465 | 300 |  |  | -
Stem, ch 0–1,000: front face, verticals (dwg a3) | 11a | H12 | 1 | 1 | 1 | 6625 | 21 | 185 | 6170 | 300 |  |  | -
Stem, ch 0–1,000: front face, verticals (dwg a3) | 11b | H12 | 1 | 1 | 1 | 6550 | 21 | 185 | 6090 | 300 |  |  | -
Stem, ch 0–1,000: front face, verticals (dwg a3) | 11c | H12 | 1 | 1 | 1 | 6450 | 21 | 185 | 6010 | 300 |  |  | -
Stem, ch 0–1,000: front face, verticals (dwg a3) | 11d | H12 | 1 | 1 | 1 | 6375 | 21 | 185 | 5930 | 300 |  |  | -
Stem, ch 0–1,000: front face, verticals (dwg a3) | 11e | H12 | 1 | 1 | 1 | 6300 | 21 | 185 | 5850 | 300 |  |  | -
Stem, ch 0–1,000: front face, verticals (dwg a3) | 11f | H12 | 1 | 1 | 1 | 6225 | 21 | 185 | 5770 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12a | H12 | 1 | 1 | 1 | 6150 | 21 | 185 | 5700 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12b | H12 | 1 | 1 | 1 | 6075 | 21 | 185 | 5625 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12c | H12 | 1 | 1 | 1 | 6000 | 21 | 185 | 5555 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12d | H12 | 1 | 1 | 1 | 5925 | 21 | 185 | 5480 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12e | H12 | 1 | 1 | 1 | 5850 | 21 | 185 | 5410 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12f | H12 | 1 | 1 | 1 | 5775 | 21 | 185 | 5335 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12g | H12 | 1 | 1 | 1 | 5725 | 21 | 185 | 5265 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12h | H12 | 1 | 1 | 1 | 5650 | 21 | 185 | 5190 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12i | H12 | 1 | 1 | 1 | 5575 | 21 | 185 | 5120 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12j | H12 | 1 | 1 | 1 | 5500 | 21 | 185 | 5045 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12k | H12 | 1 | 1 | 1 | 5425 | 21 | 185 | 4975 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12l | H12 | 1 | 1 | 1 | 5350 | 21 | 185 | 4900 | 300 |  |  | -
Stem, ch 1,000–3,000: front face, verticals (dwg a3) | 12m | H12 | 1 | 1 | 1 | 5275 | 21 | 185 | 4830 | 300 |  |  | -
Stem, ch 3,000–5,000: front face, verticals (dwg a3) | 13a | H12 | 1 | 1 | 1 | 5200 | 21 | 185 | 4755 | 300 |  |  | -
Stem, ch 3,000–5,000: front face, verticals (dwg a3) | 13b | H12 | 1 | 1 | 1 | 5050 | 21 | 185 | 4610 | 300 |  |  | -
Stem, ch 3,000–5,000: front face, verticals (dwg a3) | 13c | H12 | 1 | 1 | 1 | 4900 | 21 | 185 | 4460 | 300 |  |  | -
Stem, ch 3,000–5,000: front face, verticals (dwg a3) | 13d | H12 | 1 | 1 | 1 | 4750 | 21 | 185 | 4310 | 300 |  |  | -
Stem, ch 3,000–5,000: front face, verticals (dwg a3) | 13e | H12 | 1 | 1 | 1 | 4600 | 21 | 185 | 4160 | 300 |  |  | -
Stem, ch 3,000–5,000: front face, verticals (dwg a3) | 13f | H12 | 1 | 1 | 1 | 4450 | 21 | 185 | 4010 | 300 |  |  | -
Stem, ch 3,000–5,000: front face, verticals (dwg a3) | 13g | H12 | 1 | 1 | 1 | 4300 | 21 | 185 | 3860 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14a | H12 | 1 | 1 | 1 | 4150 | 21 | 185 | 3710 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14b | H12 | 1 | 1 | 1 | 4075 | 21 | 185 | 3620 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14c | H12 | 1 | 1 | 1 | 3975 | 21 | 185 | 3530 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14d | H12 | 1 | 1 | 1 | 3900 | 21 | 185 | 3440 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14e | H12 | 1 | 1 | 1 | 3800 | 21 | 185 | 3350 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14f | H12 | 1 | 1 | 1 | 3700 | 21 | 185 | 3260 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14g | H12 | 1 | 1 | 1 | 3625 | 21 | 185 | 3170 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14h | H12 | 1 | 1 | 1 | 3525 | 21 | 185 | 3080 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14i | H12 | 1 | 1 | 1 | 3450 | 21 | 185 | 2990 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14j | H12 | 1 | 1 | 1 | 3350 | 21 | 185 | 2900 | 300 |  |  | -
Stem, ch 5,000–7,000: front face, verticals (dwg a3) | 14k | H12 | 1 | 1 | 1 | 3250 | 21 | 185 | 2810 | 300 |  |  | -
Stem, ch 7,000–8,000: front face, verticals (dwg a3) | 15a | H12 | 1 | 1 | 1 | 3175 | 21 | 185 | 2720 | 300 |  |  | -
Stem, ch 7,000–8,000: front face, verticals (dwg a3) | 15b | H12 | 1 | 1 | 1 | 3075 | 21 | 185 | 2630 | 300 |  |  | -
Stem, ch 7,000–8,000: front face, verticals (dwg a3) | 15c | H12 | 1 | 1 | 1 | 2975 | 21 | 185 | 2530 | 300 |  |  | -
Stem, ch 7,000–8,000: front face, verticals (dwg a3) | 15d | H12 | 1 | 1 | 1 | 2875 | 21 | 185 | 2430 | 300 |  |  | -
Base, ch 0–1,000: bottom, full width (dwg a4) | 16 | H16 | 1 | 3 | 3 | 4500 | 21 | 150 | 4250 | 150 |  |  | -
Base, ch 1,000–3,000: bottom, full width (dwg a4) | 17 | H12 | 1 | 7 | 7 | 3425 | 21 | 150 | 3150 | 150 |  |  | -
Base, ch 3,000–5,000: bottom, full width (dwg a4) | 18 | H12 | 1 | 7 | 7 | 2825 | 21 | 150 | 2550 | 150 |  |  | -
Base, ch 5,000–7,000: bottom, full width (dwg a4) | 19 | H12 | 1 | 6 | 6 | 2425 | 21 | 150 | 2150 | 150 |  |  | -
Base, ch 7,000–8,000: bottom, full width (dwg a4) | 20 | H12 | 1 | 2 | 2 | 1725 | 21 | 150 | 1450 | 150 |  |  | -
Base, ch 0–1,000: bottom, toe side (extra) (dwg a5) | 21 | H16 | 1 | 3 | 3 | 2775 | 11 | 2635 | 150 |  |  |  | -
Base, ch 1,000–3,000: bottom, toe side (extra) (dwg a5) | 22 | H12 | 1 | 7 | 7 | 2050 | 11 | 1905 | 150 |  |  |  | -
Base, ch 3,000–5,000: bottom, toe side (extra) (dwg a5) | 23 | H12 | 1 | 6 | 6 | 1650 | 11 | 1505 | 150 |  |  |  | -
Base, ch 5,000–7,000: bottom, toe side (extra) (dwg a5) | 24 | H12 | 1 | 6 | 6 | 1550 | 11 | 1405 | 150 |  |  |  | -
Base, ch 7,000–8,000: bottom, toe side (extra) (dwg a5) | 25 | H12 | 1 | 2 | 2 | 1350 | 11 | 1205 | 150 |  |  |  | -
Base, ch 0–1,000: top of heel (extra) (dwg a7) | 26 | H16 | 1 | 3 | 3 | 4175 | 99 | 150 | 2530 | 600 | 915 |  | -
Base, ch 1,000–3,000: top of heel (extra) (dwg a7) | 27 | H12 | 1 | 6 | 6 | 3250 | 99 | 150 | 1925 | 500 | 685 |  | -
Base, ch 3,000–5,000: top of heel (extra) (dwg a7) | 28 | H12 | 1 | 7 | 7 | 2825 | 99 | 150 | 1725 | 400 | 430 | 150 | -
Base, ch 5,000–7,000: top of heel (extra) (dwg a7) | 29 | H12 | 1 | 6 | 6 | 2425 | 21 | 150 | 2150 | 150 |  |  | -
Base, ch 7,000–8,000: top of heel (extra) (dwg a7) | 30 | H12 | 1 | 2 | 2 | 1725 | 21 | 150 | 1450 | 150 |  |  | -
Base, ch 0–1,000: top, full width (dwg a8) | 31 | H16 | 1 | 3 | 3 | 4525 | 99 | 150 | 2530 | 600 | 1140 | 150 | -
Base, ch 1,000–3,000: top, full width (dwg a8) | 32 | H12 | 1 | 7 | 7 | 3425 | 99 | 150 | 1925 | 500 | 730 | 150 | -
Base, ch 3,000–5,000: top, full width (dwg a8) | 33 | H12 | 1 | 7 | 7 | 2825 | 99 | 150 | 1725 | 400 | 430 | 150 | -
Base, ch 5,000–7,000: top, full width (dwg a8) | 34 | H12 | 1 | 5 | 5 | 2425 | 21 | 150 | 2150 | 150 |  |  | -
Base, ch 7,000–8,000: top, full width (dwg a8) | 35 | H12 | 1 | 3 | 3 | 1725 | 21 | 150 | 1450 | 150 |  |  | -
Base, ch 0–8,000: bottom, along the wall (dwg a6) | 36a | H12 | 1 | 18 | 18 | 1075 | 00 | 1075 |  |  |  |  | -
Base, ch 0–8,000: bottom, along the wall (dwg a6) | 36b | H12 | 1 | 6 | 6 | 850 | 00 | 850 |  |  |  |  | -
Base, ch 0–8,000: bottom, along the wall (dwg a6) | 37a | H10 | 1 | 8 | 8 | 7075 | 00 | 7075 |  |  |  |  | -
Base, ch 0–8,000: bottom, along the wall (dwg a6) | 37b | H10 | 1 | 4 | 4 | 6075 | 00 | 6075 |  |  |  |  | -
Base, ch 0–8,000: bottom, along the wall (dwg a6) | 37c | H10 | 1 | 2 | 2 | 4075 | 00 | 4075 |  |  |  |  | -
Base, ch 0–8,000: bottom, along the wall (dwg a6) | 37d | H10 | 1 | 4 | 4 | 2075 | 00 | 2075 |  |  |  |  | -
Base, ch 0–8,000: top of heel, along the wall (dwg a6) | 38 | H12 | 1 | 14 | 14 | 850 | 00 | 850 |  |  |  |  | -
Base, ch 0–8,000: top of heel, along the wall (dwg a6) | 39a | H10 | 1 | 5 | 5 | 2850 | 00 | 2850 |  |  |  |  | -
Base, ch 0–8,000: top of heel, along the wall (dwg a6) | 39b | H10 | 1 | 23 | 23 | 1850 | 00 | 1850 |  |  |  |  | -
Base, ch 0–8,000: top of toe, along the wall (dwg a6) | 40 | H12 | 1 | 6 | 6 | 850 | 00 | 850 |  |  |  |  | -
Base, ch 0–8,000: top of toe, along the wall (dwg a6) | 41a | H10 | 1 | 1 | 1 | 2850 | 00 | 2850 |  |  |  |  | -
Base, ch 0–8,000: top of toe, along the wall (dwg a6) | 41b | H10 | 1 | 7 | 7 | 1850 | 00 | 1850 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42a | H10 | 1 | 12 | 12 | 2850 | 00 | 2850 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42b | H10 | 1 | 1 | 1 | 2600 | 00 | 2600 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42c | H10 | 1 | 1 | 1 | 2250 | 00 | 2250 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42d | H10 | 1 | 1 | 1 | 1875 | 00 | 1875 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42e | H10 | 1 | 44 | 44 | 1850 | 00 | 1850 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42f | H10 | 1 | 1 | 1 | 1725 | 00 | 1725 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42g | H10 | 1 | 1 | 1 | 1575 | 00 | 1575 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42h | H10 | 1 | 1 | 1 | 1525 | 00 | 1525 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42i | H10 | 1 | 1 | 1 | 1375 | 00 | 1375 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42j | H10 | 1 | 1 | 1 | 1200 | 00 | 1200 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42k | H10 | 1 | 1 | 1 | 1175 | 00 | 1175 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42l | H10 | 1 | 1 | 1 | 1000 | 00 | 1000 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42m | H10 | 1 | 1 | 1 | 850 | 00 | 850 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42n | H10 | 1 | 1 | 1 | 800 | 00 | 800 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42o | H10 | 1 | 1 | 1 | 650 | 00 | 650 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 42p | H10 | 1 | 1 | 1 | 450 | 00 | 450 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 43a | H12 | 1 | 29 | 29 | 850 | 00 | 850 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 43b | H12 | 1 | 1 | 1 | 775 | 00 | 775 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 43c | H12 | 1 | 1 | 1 | 475 | 00 | 475 |  |  |  |  | -
Stem, ch 0–8,000: earth face, along the wall (dwg a9) | 43d | H12 | 1 | 1 | 1 | 400 | 00 | 400 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44a | H10 | 1 | 10 | 10 | 7075 | 00 | 7075 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44b | H10 | 1 | 1 | 1 | 6850 | 00 | 6850 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44c | H10 | 1 | 1 | 1 | 6825 | 00 | 6825 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44d | H10 | 1 | 1 | 1 | 6475 | 00 | 6475 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44e | H10 | 1 | 1 | 1 | 6100 | 00 | 6100 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44f | H10 | 1 | 1 | 1 | 5750 | 00 | 5750 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44g | H10 | 1 | 1 | 1 | 5400 | 00 | 5400 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44h | H10 | 1 | 1 | 1 | 5025 | 00 | 5025 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44i | H10 | 1 | 1 | 1 | 4675 | 00 | 4675 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44j | H10 | 1 | 1 | 1 | 4300 | 00 | 4300 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44k | H10 | 1 | 1 | 1 | 3950 | 00 | 3950 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44l | H10 | 1 | 1 | 1 | 3600 | 00 | 3600 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44m | H10 | 1 | 1 | 1 | 3225 | 00 | 3225 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44n | H10 | 1 | 1 | 1 | 2875 | 00 | 2875 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44o | H10 | 1 | 1 | 1 | 2850 | 00 | 2850 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44p | H10 | 1 | 1 | 1 | 2500 | 00 | 2500 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44q | H10 | 1 | 1 | 1 | 2150 | 00 | 2150 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44r | H10 | 1 | 1 | 1 | 1800 | 00 | 1800 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44s | H10 | 1 | 1 | 1 | 1425 | 00 | 1425 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 44t | H10 | 1 | 1 | 1 | 1075 | 00 | 1075 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 45a | H12 | 1 | 1 | 1 | 1475 | 00 | 1475 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 45b | H12 | 1 | 1 | 1 | 1125 | 00 | 1125 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 45c | H12 | 1 | 27 | 27 | 1075 | 00 | 1075 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 45d | H12 | 1 | 1 | 1 | 775 | 00 | 775 |  |  |  |  | -
Stem, ch 0–8,000: front face, along the wall (dwg a9) | 45e | H12 | 1 | 1 | 1 | 400 | 00 | 400 |  |  |  |  | -
Total mass (kg)

## BS 8666 points to confirm
Bar schedule WW101A: points to confirm with the designer
Sample. A real wing wall drawing re-presented to BS 8666:2020, every bar scheduled; project details removed. AI first pass, checked and signed off by an engineer. arched.ai
Ref | Point | Basis adopted meanwhile
Q-01 | a1 and a2 at ch 0 to 1,000 are H20. Their top leg across the 300 mm stem top would be 185 mm, below the 190 mm minimum end projection P for H20 (BS 8666 Table 2). | Scheduled as shape 11 with no top leg (marks 01a to 01c, 06a to 06c). The a3 top legs still cross the stem top. Confirm, or detail a U-bar cap.
Q-02 | Distribution bars change from H12 to H10 at ch 1,000. Drawing note 7 laps them by the greater of 12 diameters and 300 mm, shorter than a full tension lap to BS EN 1992-1-1. | Lapped 300 mm as drawn on the front face and base underside, where the bars run through. Confirm the lap.
Q-03 | The drawing does not show how the distribution bars meet the abutment. | Taken stopping 75 mm off the abutment face. If they are to anchor into the abutment, they lengthen by the anchorage.
Q-04 | No U-bars at the free end and no edge bar along the sloping top are shown. | None scheduled. Bars stop 75 mm off the end face and 40 mm (square) under the top.
Q-05 | a2 has the same shape as a1 and no curtailment level. | Taken full height, offset half a spacing from a1.
Q-06 | a7 (heel top, extra) is anchored 57 diameters past the stem (drawing note 6). Length past the rear face of the stem: 830 mm along the bar at ch 3,000 to 5,000 (including the kink onto the toe slope) and 725 straight at ch 5,000 to 7,000, both over the 684 needed; at ch 7,000 to 8,000 only 525. In the last three bands a7 also matches a8 bar for bar. | From ch 5,000 a7 is scheduled as a full-width U (marks 29 and 30). At ch 7,000 to 8,000: 525 straight plus a 150 down leg is 675 along the bar, 9 mm short of 684 unless the bend is counted. Confirm, or detail a hook; and confirm the doubled top steel in those bands is intended.
Q-07 | a3 is 12 @ 300 in the 4.5 to 3.5 m band, against 12 @ 145 above and 12 @ 180 below. | Scheduled as drawn. It looks like a drawing error (150?); confirm.
Q-08 | Stem verticals are drawn continuous from the base, so they stand 6.5 m out of the base pour. | Scheduled as drawn. We suggest starter bars to a kicker with lapped verticals; on the answer we reschedule the stem.
Q-09 | The earth face and the base top step at ch 1,000, 3,000 and 5,000. | Bars on those faces stop 75 mm each side of each step. Confirm whether the steps are joints or need continuity bars.
Q-10 | Chairs and spacers for the base top mat are not shown. | Not scheduled: by the contractor.
Q-11 | For Gulf use: 40 mm cover to the front face. | Scheduled as drawn. Check it against the exposure class in the project specification.